## SME Clarifications
ID | Clarification Area | Question to Ask SME | What the Files Say / Gap | Agentic Avengers Proposed Recommendation | Blocks Feature? | Approval Needed From | When Needed | Dev's response | Ranjit's reponse
1 | Critical question definition | What exactly makes a question critical for each function/skill? | Dataset v2 has a critical_flag but does not define it; RD has no critical-question concept. | A question is critical only when a wrong answer indicates a material control, compliance, audit, regulatory, safety, or policy failure—not merely inefficiency. | Yes | Tower / Skill SME | Before finalizing question-generation and scoring rules | Critical questions are the difficult questions in RD, with situations and need more research or dip dive to get the answers.
2 | Critical question proportion | Out of the assessment set, how many questions may or must be critical? | No approved ratio is stated. The current CIS prompt allows at most 1 of 5, but this is a team rule, not a source rule. | Use AI to recommend criticality, cap it through configuration, and require SME confirmation. Validate whether 1 in 5 is acceptable. | Yes | Tower / Skill SME | Before using critical failure in the demo | 30% of the datasets
3 | Critical failure consequence | Does answering a critical question incorrectly automatically fail the assessment, cap the proficiency level, or only trigger review? | Dataset v2 contains critical-failure fields but no authoritative formula; RD is silent. | Do not auto-fail until approved. For Phase I, flag for SME/manager review unless the SME confirms an auto-fail rule. | Yes | Assessment SME / Business owner | Before scoring logic is finalized | Not fail. It will be treated as not answered correctly however it should be part of insights.
4 | Skill selection | If a role has more skills than the assessment can cover, which skills should be included? | Dataset v2 commonly shows 10 skills but does not explain how those 10 are selected. | Use role-critical and target-proficiency skills from the approved role-skill matrix; allow SME confirmation before generation. | Yes | Role / Tower SME | Before blueprint configuration | Yes, the assesment should cover the topics/areas to cover all skill requried for the role.
5 | Question distribution | How should the total questions be distributed across the selected skills? | Dataset v2 shows 20 questions and 10 skills but does not state equal, weighted, or risk-based allocation. | Use a configurable skill-by-question matrix. Do not assume 2 per skill without approval. | Yes | Assessment SME | Before question-generation loop | 30% - difficult, 40% - moderate - 30% easy
6 | Question approval rubric | What exact criteria must an SME use to Approve, Reject, Rewrite, or Regenerate a question? | The files imply relevance, correctness and review status but do not provide an approved rubric or threshold. | Approve only when skill relevance, target-level alignment, correctness, clarity, unbiased wording, plausible distractors, and source traceability pass. SME to validate rubric/threshold. | Yes | Assessment SME | Before SME review screen is finalized | Approve - if it meets the expected critieria of the answers. Rejects - does not meets the expected critieria Rewrite or re-generate - if the question is vague / does not gives the clarity then re-write or re-generation is needed.
7 | Minimum approved question threshold | Is readiness based only on reaching 20 approved questions, or must skill and difficulty coverage also be complete? | Dataset v2 has records marked ready below target, creating a contradiction. | Require both approved count and blueprint coverage. SME/data owner must correct or accept exceptions. | Yes | Assessment SME / Dataset owner | Before scheduling gate | The questions not necessarily is 20, these could be increased based on the need of the business. For the start, let's keep 20.
8 | AI confidence usage | What should happen at different confidence levels? | Dataset v2 has ai_confidence but no scale, threshold, or action. The current prompt defines indicative ranges only. | Use confidence for triage only; low-confidence questions cannot be approved without explicit SME review. SME/RAI owner to approve thresholds. | No | Assessment SME / RAI owner | Before any automation based on confidence
9 | Subjective scoring rubric | How should free-text or scenario answers be scored, including criteria, weights and thresholds? | No explicit scoring formula or division of AI/human responsibility exists. | Use an SME-approved analytic rubric; AI may pre-score with evidence citations, but human validation remains final for Phase I. | Yes | Behavioural Skill SME / RAI owner | Before subjective scoring is implemented | A repository can be provided, currently we have the trainig modules located at MyAcademy to support the trainig contents which can in turn should help to validate the situations based question and answers.
10 | Evidence requirements | What evidence types are acceptable for each demo skill and proficiency level? | RD gives broad examples but no complete evidence matrix, recency rule, or threshold. | Create a skill-level evidence matrix covering type, mandatory metadata, recency, confidentiality and acceptance criteria. | Yes | Skill SME | Before evidence upload/validation demo | Validation against the My academy training modules. The output should be shown in terms of the answers matching against the documents. (more than 90% match)
11 | Manager evidence rubric | What objective rule should the manager use to confirm, return, or reject evidence? | RD requires manager confirmation but provides no standardized approval rubric. | Use an approved rubric for authenticity, relevance, complexity, impact, recency and demonstrated level; require comments for return/reject. | Yes | Skill SME / HR governance | Before manager validation screen is finalized | Accept more than 90%, reject less than 90% for difficult situation based questions. Verifying it against the MyAcademy documents.
12 | Expert-level decision | What exact evidence qualifies someone as Expert, and is manager confirmation sufficient? | RD says a high score alone is insufficient and mentions complexity, impact, governance and coaching, but does not quantify or set final authority. | Require evidence plus manager validation and independent SME calibration for Expert or disputed cases. | Yes | RD / Skill SME | Before publishing Expert outcomes | An expert should be able to demonstrate highest level of knowledge for each topics covered in the Assessment framework. There should be multi-fold question in those situations.
13 | Reassessment content | When an employee retakes an assessment, how much of the question set must be new and can previously failed items reappear? | The files support movement over time but do not define reassessment/question reuse rules. | Rotate questions, preserve all attempts, and let the SME approve a minimum new-question percentage. | No | Assessment SME | Needed for future reassessment; optional for Phase I demo | Anything between 0-30% old and 70% new atleast.
14 | Final level formula | How should objective score, behavioural score, evidence and manager/SME validation combine into the final proficiency level? | No complete authoritative formula exists across the two files. | Keep test result provisional; publish the validated level only after the approved scoring/evidence rules are met. | Yes | Assessment SME / Proficiency owner | Before final result and TNI logic | Objective Score - For Basic meeting criteria more than >80%-<95% correct answers. For Expert =>95%. Behariour/Principle: The Principle defination should match with the demonstrated competency >80%-<90% for meeting basic criteria. For Expert =>90%.

## Data Findings
source | area | severity | finding | evidence | Dev's feedback
Dataset v2 | Skill_Master | Blocking | 13 R2R skills are missing from Skill_Master entirely | Skill_Master holds 28 skills (16 AP + 12 O2C) and no R2R. Role_Skill_Map references 13 distinct R2R skill_ids across 30 rows.
Dataset v2 | Role_Skill_Map | Blocking | R2R rows carry no behaviour indicator and no capability | All 30 of 30 R2R rows have behavior_indicator blank and capability blank. Target levels (3, 4) ARE present.
RD Input Pack | People data | Blocking | The pack supplies no people data at all | No users, no assessment results, no gaps, no movement history. Competency framework only. | Currently we need to pick dummy ones, with no assessment results those could be build dummy as well to build the overall development plan with the identified gaps.